| **DATE** | **ACTIONS** | **Program or Agency Involved** | **NOTES** |
| --- | --- | --- | --- |
| **5/18/21** | Site access granted. | DEP-Fire Academy of the South | DEP secured site access. DEP site number: ERIC\_17235. |
| **6/23/21** | Site reconnaissance performed at the site with Academy representatives and a DEP contractor. | DEP-Fire Academy of the South | Site reconnaissance performed. PFAS samples collected from two surface water bodies and a supply well. SIS-2021-06-25-01 |
| **7/01/21** | DEP Central Laboratory certified results released. | DEP Central Laboratory | Elevated PFAS levels in the surface water bodies. The potable well was nondetect for all PFAS analytes. |
| **8/06/21** | Draft work plan released by State contractor. | DEP - State Contractor | Prospective soil, ground and surface water sample locations identified. |
| **10/11/21** | Final work plan released by State Contractor. Initial soil sampling and DPT work scheduled for week of 11/15/21 | DEP-State Contractor-Fire Academy of the South | Work Plan sent to Fire Academy of the South |
| **Nov.-Dec. 2021** | State Contractor collects soil and surface water samples from 110+ locations | DEP - State Contractor | PFAS contamination in soils and surface water spread broadly across facility |
| **12/13/21** | SIS installs 8 shallow monitor wells at the site and collects HPT data | DEP - State Contractor | Monitor wells are water table intercept wells |
| **February 2022** | DPT rig scheduled for collection of screen-points | DEP - State Contractor |  |
| **March 14, 2022** | Sonic Rig scheduled for installation of deep wells | DEP - State Contractor |  |
| **August 2022** | Golder Issues SAR  | DEP - State Contractor | PFAS is spread across site in groundwater, soils, sediments and surface water |
| **March 2023** | Second Phase of Assessment begins. Shallow monitor wells, vertical profiling and sediment and surface water sampling including offsite locations | DEP - State Contractor | Samples will be collected from adjacent Alden Road Exceptional School |
| **November 2023** | Supplemental SAR released | DEP - State Contractor | Groundwater and soil samples collected from Alden Road exceptional school not contaminated. Concentrations of PFAS decrease south of canal below PGCTL of 70 ng/L. |
| **January 2024** | WSP developing CEF for three different source remediation scenarios  | DEP - State Contractor | WSP and DEP scheduled to meet with FAOS and FSCJ personnel to discuss SSAR and remediation scenarios the week of February 12th 2024 |
| **January 2024** | WSP developing CEF for assessment of impacted potable wells located south of Beach Blvd | DEP - State Contractor | Some potable wells located along Versailles Street exceed PGCTL |
| **February 2025** | WSP resamples existing monitor well network | DEP-WSP | DEP Lab results sent 3-13-2025. Awaiting SSAR |