| DATE | ACTIONS | Program or Agency Involved | NOTES |
| --- | --- | --- | --- |
| 8/02/19 | Contacted fire chief regarding acquiring site access. | DEP, Miami-Dade College | To request site access and answer questions. DEP Site Number: ERIC_7421 |
| 9/18/19 | Received information that assessment has already been performed at the facility. | DEP, Miami-Dade College |  |
| 10/03/19 | Results provided by the College’s consultants indicate that all seven monitoring well locations exceed the provisional PFOA+PFOS GCTL, which means additional sampling is needed. Soil samples collected at the monitoring well locations from 0-0.5’ and 0.5-2’ did not exceed Residential or Commercial/Industrial SCTLs, however, there were exceedances of the Leachability SCTL in multiple samples. | DEP, Miami-Dade College, DOH | DOH notified to conduct private well sampling and necessary notifications. |
| 2/5/20 | Five additional monitoring wells were installed by College’s consultants in December 2019. Results have confirmed exceedances of PFOA+PFOS GCTL in some areas, meaning continued assessment is warranted. Consultant is conducting additional on-site sampling soon. Miami-Dade DERM will be sampling on-site irrigation wells for PFAS-related compounds in upcoming weeks. | DEP, Miami-Dade College, DOH, DERM | DOH actively canvassing nearby area for private supply wells. DEP will take lead role in further PFAS-related work in upcoming months. |
| 7/08/21 | Work Plan submitted by State Contractor | State Contactor, DEP | Site assessment activities including the collection of soil and sediment samples to commence the week of August 30th, 2021. |
| 08/30/21 | State Contractor collected soil, sediment and surface water samples from site | State Contractor, Miami-Dade College | State Contractor collected samples from four areas of concern (AOC) outlined in the Work Plan |
| 10/06/21 | DEP Laboratory released certified results from 08/30/21 soil, sediment and surface water sampling | DEP Laboratory |  |
| 10/11/21 | State Contractor installed shallow monitor wells and collected screen-points from site using DPT rig | State Contractor, Miami-Dade College | State Contractor collected samples from four areas of concern (AOC) outlined in the Work Plan |
| 02/01/22 | Sonic rig on-site to install six deep monitor wells to a depth of 80’ BLS | State Contractor, Miami-Dade College |  |
| 02/28/22 | Golder on-site to collect ground water samples from shallow and deep monitor wells | State Contractor, Miami-Dade College | State Contractor collected samples from four areas of concern (AOC) outlined in the Work Plan |
| 06/01/22 | Golder issues Site Assessment Report | State Contractor, Miami-Dade College | Widespread PFAS soil contamination in AOC-1. Widespread PFAS ground water contamination across entire site. Golder is preparing a second phase of assessment activities including offsite |
| 01/02/23 | Golder/WSP begins second phase of assessment. Soil sampling, DPT vertical profiling and installation of 8 on site shallow monitor wells and three offsite shallow monitor wells. Also includes 2 deep offsite monitor wells | State Contractor Miami Dade College | Newly installed monitor wells to be sampled June 2023 |
| 10/01/23 | Supplemental SAR released | State Contractor | Offsite groundwater to east and South of main campus show PFAS just below PGCTL |
| January 2024 | WSP developing CEF for three different source remediation scenarios | State Contractor |  |
| February 2025 | WSP begins the third phase of assessment. 2 deep wells and 10 shallow monitor wells and resampling of monitor wells. Work is halted as MDSC wants a separate site access agreement with WSP. Currently waiting on MDSC to provide site access agreement for review | DEP-WSP |  |
| November 2025 | Site Access Agreement | DEP-MDC | After much work an agreed upon SAA has been signed by MDC personnel. MDC has not provided the SAA to DEP despite frequent requests to do so. Site remains in limbo. |