## Instructions
The milestone workbook is intended to replace the previous milestone program dated April 25, 2005. The workbook complies with all sections of the most recent version of the Remedial Action Initiative dated February 15, 2008. Instructions for use Only shaded cells are able to be filled by the user. All facility information, including the facility name and identification number as well as baseline sampling information including date, key well designation, contaminant groups, and concentrations, are included on the first tab, titled "Milestone Wells". All of this information will be populated on the individual well sheets automatically. In addition to the facility and baseline sampling information, the user must select the Active Remediation Goal from the dropdown menu (GCTLs, NADCs, 90% reduction from baseline, or 70% of NADCs) and enter the Estimated Active Remediation Time in years. Each key monitoring well will have its own sheet to be completed for all subsequent O&M Reports. The only information that will be required each reporting period will be the sampling date and the sampling results. Note that the results are not necessarily reported as individual contaminants, but as the contaminant groups highlighted in the Remedial Action Initiative. The target concentrations are calculated based on the sampling date once that date is entered. If any concentration exceeds the target concentration the cell will automatically change to bold type with no shading. Milestone graphs will be auto-populated with the milestone projections (using the system startup date as day 0), actual concentrations and sampling dates, and the anticipated end of active remediation. Contaminant groups 5, 6, and 7 are not included on the graph due to high variability of concentrations and should be compared to the milestones only in the table. The main milestone well tab in addition to each key well page will print out on one page each. If desired the milestone graph may be printed separately for clarity purposes. All used pages should be submitted in each applicable remedial action report (Startup and O&M).

## Milestone Wells
MILESTONE SCHEDULE
Facility Name | ACME |  |  | Baseline Sampling Date |  |  | 2011-01-01
Facility ID # | 123456789 |  |  | System Startup Date |  |  | 2011-01-15
Baseline Constituent Concentrations (ug/l)
Contaminant Group Per March 1, 2004 RAI |  | Group 1 | Group 2 |  |  |  | Group 3 |  |  |  | Group 4 | Group 5 | Group 6 | Group 7
Milestone Well # | Monitoring Wells | Benzene | Toluene | Ethyl-benzene | Xylenes | Sum TEX | Naph-thalene | 1-Methyl Naph. | 2-Methyl Naph. | Sum Naphs | MTBE | TRPH | PAH (I)1 | PAH (II)2
First Well | MW-1 | 800 | 60 | 90 | 800 | 950 | 150 | 33 | 60 | 243 | 900
Second Well | MW-2 | 2000 | 16000 | 1300 | 8800 | 26100 | 260 | 65 | 120 | 445 | 800
Third Well | MW-3 | 2500 | 17000 | 1200 | 8200 | 26400 | 160 | 29 | 59 | 248 | 700
Fourth Well | MW-4 | 3200 | 13000 | 650 | 4700 | 18350 | 150 | 32 | 59 | 241 | 600
Fifth Well | MW-5 | 21000 | 31000 | 1100 | 8300 | 40400 | 170 | 41 | 72 | 283 | 545
Sixth Well | MW-6 | 16000 | 26000 | 800 | 5900 | 32700 | 160 | 33 | 59 | 252 | 3210
Defined Cleanup Target Levels (ug/l)
Contaminant Group Per March 1, 2004 RAI |  | Group 1 | Group 2 |  |  |  | Group 3 |  |  |  | Group 4 | Group 5 | Group 6 | Group 7
Cleanup Target |  | Benzene | Sum: Toluene, Ethylbenzene, Total Xylenes |  |  |  | Sum: Naphthalenes |  |  |  | MTBE | TRPH | PAH (I)1 | PAH (II)2
Groundwater Cleanup Target Level (ug/l) |  | 1 | 90 |  |  |  | 70 |  |  |  | 20 | 5000
Natural Attenuation Default Conc. (ug/l) |  | 100 | 900 |  |  |  | 700 |  |  |  | 200 | 50000
70% Natural Attenuation Default Conc. (ug/l) |  | 70 | 630 |  |  |  | 490 |  |  |  | 140 | 35000
90% Baseline Reduction (ug/l)
First Well | MW-1 | 80 | 95 |  |  |  | 24.3 |  |  |  | 90 | 0 | 0 | 0
Second Well | MW-2 | 200 | 2610 |  |  |  | 44.5 |  |  |  | 80 | 0 | 0 | 0
Third Well | MW-3 | 250 | 2640 |  |  |  | 24.8 |  |  |  | 70 | 0 | 0 | 0
Fourth Well | MW-4 | 320 | 1835 |  |  |  | 24.1 |  |  |  | 60 | 0 | 0 | 0
Fifth Well | MW-5 | 2100 | 4040 |  |  |  | 28.3 |  |  |  | 54.5 | 0 | 0 | 0
Sixth Well | MW-6 | 1600 | 3270 |  |  |  | 25.2 |  |  |  | 321 | 0 | 0 | 0
Selected Active Remediation Goal
| 1 | 1 | 90 |  |  |  | 70 |  |  |  | 20 | 5000 | 0 | 0
|  | 1 | 90 |  |  |  | 70 |  |  |  | 20 | 5000 | 0 | 0
|  | 1 | 90 |  |  |  | 70 |  |  |  | 20 | 5000 | 0 | 0
|  | 1 | 90 |  |  |  | 70 |  |  |  | 20 | 5000 | 0 | 0
|  | 1 | 90 |  |  |  | 70 |  |  |  | 20 | 5000 | 0 | 0
|  | 1 | 90 |  |  |  | 70 |  |  |  | 20 | 5000 | 0 | 0
Estimated Active Remediation Time |  | 2 | years
Milestones are based on pre-startup baseline sampling per Section C.2 of the March 1, 2004 FDEP RAI.
Groundwater Cleanup Target Levels and Natural Attenuation Default Concentrations (NADC) as established in Chapter 62-777, F.A.C.
1Sum of Benzo(a)anthracene, Benzo(a)pyrene, Benzo(b)flouranthene, Benzo(k)flouranthene, Dibenz(a,h)anthracene, Chrysene, and Indeno(1,2,3-cd)pyrene.
2Sum of other PAH's not included in Group 3 or Group 6

## Well 1
Monitoring Well |  | MW-1 |  | Facility Name |  | ACME |  |  | Baseline Sampling Date |  |  | 2011-01-01
|  |  |  | Facility ID # |  | 123456789 |  |  | System Startup Date |  |  | 2011-01-15
Constituent Concentration Group Milestones (ug/l)
Projected Cleanup Time (yrs) | Actual Sampling Date | Actual Cleanup Time (yrs) |  | Group 1 |  | Group 2 |  | Group 3 |  | Group 4 |  | Group 5 |  | Group 6 |  | Group 7
|  |  |  | Benzene |  | Sum Toluene, Ethylbenzene, & Xylenes |  | Naphthalenes |  | MTBE |  | TRPH |  | PAH (I) |  | PAH (II)
|  |  |  | Proj. | Actual | Proj. | Actual | Proj. | Actual | Proj. | Actual | Proj. | Actual | Proj. | Actual | Proj. | Actual
0 | 2011-01-01 | 0 | 0 | 800 | 800 | 950 | 950 | 243 | 243 | 900 | 900 | NA | NA | NA | NA | NA | NA
0.25 | 2011-04-16 | 0.24932 | 0.24932 | 700.3986 | 800 | 842.7945 | 400 | 221.4342 | 150 | 790.3014 | 600
0.5 | 2011-08-05 | 0.55342 | 0.55342 | 578.9068 | 500 | 712.0274 | 750 | 195.1288 | 750 | 656.4932 | 600
0.75 | 2011-11-01 | 0.79452 | 0.79452 | 482.589 | 301.5 | 608.3562 | 300 | 174.274 | 300 | 550.411 | 600
1 | 2012-02-02 | 1.0493 | 1.0493 | 380.7986 | 400 | 498.7945 | 400 | 152.2342 | 400 | 438.3014 | 400
1.25 |  |  | 1.25 | 300.625 | 250 | 412.5 | 250 | 134.875 | 250 | 350 | 300
1.5 |  |  | 1.5 | 200.75 | 100 | 305 | 100 | 113.25 | 100 | 240 | 300
1.75 |  |  | 1.75 | 100.875 | 102 | 197.5 | 2 | 91.625 | 2 | 130 | 100
2 |  |  | 2 | 1 | 2.5 | 90 | 3 | 70 | 3 | 20 | 21
2.25 |  |  | 2.25 | 1 |  | 90 |  | 70 |  | 20
2.5 |  |  | 2.5 | 1 |  | 90 |  | 70 |  | 20
2.75 |  |  | 2.75 | 1 |  | 90 |  | 70 |  | 20
3 |  |  | 3 | 1 |  | 90 |  | 70 |  | 20
3.25 |  |  | 3.25 | 1 |  | 90 |  | 70 |  | 20
3.5 |  |  | 3.5 | 1 |  | 90 |  | 70 |  | 20
3.75 |  |  | 3.75 | 1 |  | 90 |  | 70 |  | 20
4 |  |  | 4 | 1 |  | 90 |  | 70 |  | 20
Remediation Goal (ug/l) |  |  |  | 1 |  | 90 |  | 70 |  | 20 |  | 5000 |  | 0 |  | 0
|  | 2 |  | 0
|  | 2 |  | 950

## Well 2
Monitoring Well |  | MW-2 |  | Facility Name |  | ACME |  |  | Baseline Sampling Date |  |  | 2011-01-01
|  |  |  | Facility ID # |  | 123456789 |  |  | System Startup Date |  |  | 2011-01-15
Constituent Concentration Group Milestones (ug/l)
Projected Cleanup Time (yrs) | Actual Sampling Date | Actual Cleanup Time (yrs) |  | Group 1 |  | Group 2 |  | Group 3 |  | Group 4 |  | Group 5 |  | Group 6 |  | Group 7
|  |  |  | Benzene |  | Sum Toluene, Ethylbenzene, & Xylenes |  | Naphthalenes |  | MTBE |  | TRPH |  | PAH (I) |  | PAH (II)
|  |  |  | Proj. | Actual | Proj. | Actual | Proj. | Actual | Proj. | Actual | Proj. | Actual | Proj. | Actual | Proj. | Actual
0 | 2011-01-01 | 0 | 0 | 2000 | 2000 | 26100 | 26100 | 445 | 445 | 800 | 800 | NA | NA | NA | NA | NA | NA
0.25 | 2011-04-16 | 0.24932 | 0.24932 | 1750.8096 |  | 22857.6575 |  | 398.2534 |  | 702.7671
0.5 | 2011-08-05 | 0.55342 | 0.55342 | 1446.8521 |  | 18902.7123 |  | 341.2329 |  | 584.1644
0.75 | 2011-11-01 | 0.79452 | 0.79452 | 1205.8767 |  | 15767.2603 |  | 296.0274 |  | 490.137
1 | 2012-02-02 | 1.0493 | 1.0493 | 951.2096 |  | 12453.6575 |  | 248.2534 |  | 390.7671
1.25 |  |  | 1.25 | 750.625 |  | 9843.75 |  | 210.625 |  | 312.5
1.5 |  |  | 1.5 | 500.75 |  | 6592.5 |  | 163.75 |  | 215
1.75 |  |  | 1.75 | 250.875 |  | 3341.25 |  | 116.875 |  | 117.5
2 |  |  | 2 | 1 |  | 90 |  | 70 |  | 20
2.25 |  |  | 2.25 | 1 |  | 90 |  | 70 |  | 20
2.5 |  |  | 2.5 | 1 |  | 90 |  | 70 |  | 20
2.75 |  |  | 2.75 | 1 |  | 90 |  | 70 |  | 20
3 |  |  | 3 | 1 |  | 90 |  | 70 |  | 20
3.25 |  |  | 3.25 | 1 |  | 90 |  | 70 |  | 20
3.5 |  |  | 3.5 | 1 |  | 90 |  | 70 |  | 20
3.75 |  |  | 3.75 | 1 |  | 90 |  | 70 |  | 20
4 |  |  | 4 | 1 |  | 90 |  | 70 |  | 20
Remediation Goal (ug/l) |  |  |  | 1 |  | 90 |  | 70 |  | 20 |  | 5000 |  | 0 |  | 0
|  | 2 |  | 0
|  | 2 |  | 26100

## Well 3
Monitoring Well |  | MW-3 |  | Facility Name |  | ACME |  |  | Baseline Sampling Date |  |  | 2011-01-01
|  |  |  | Facility ID # |  | 123456789 |  |  | System Startup Date |  |  | 2011-01-15
Constituent Concentration Group Milestones (ug/l)
Projected Cleanup Time (yrs) | Actual Sampling Date | Actual Cleanup Time (yrs) |  | Group 1 |  | Group 2 |  | Group 3 |  | Group 4 |  | Group 5 |  | Group 6 |  | Group 7
|  |  |  | Benzene |  | Sum Toluene, Ethylbenzene, & Xylenes |  | Naphthalenes |  | MTBE |  | TRPH |  | PAH (I) |  | PAH (II)
|  |  |  | Proj. | Actual | Proj. | Actual | Proj. | Actual | Proj. | Actual | Proj. | Actual | Proj. | Actual | Proj. | Actual
0 | 2011-01-01 | 0 | 0 | 2500 | 2500 | 26400 | 26400 | 248 | 248 | 700 | 700 | NA | NA | NA | NA | NA | NA
0.25 | 2011-04-16 | 0.24932 | 0.24932 | 2188.4808 |  | 23120.2603 |  | 225.811 |  | 615.2329
0.5 | 2011-08-05 | 0.55342 | 0.55342 | 1808.4959 |  | 19119.6986 |  | 198.7452 |  | 511.8356
0.75 | 2011-11-01 | 0.79452 | 0.79452 | 1507.2466 |  | 15948.0822 |  | 177.2877 |  | 429.863
1 | 2012-02-02 | 1.0493 | 1.0493 | 1188.8808 |  | 12596.2603 |  | 154.611 |  | 343.2329
1.25 |  |  | 1.25 | 938.125 |  | 9956.25 |  | 136.75 |  | 275
1.5 |  |  | 1.5 | 625.75 |  | 6667.5 |  | 114.5 |  | 190
1.75 |  |  | 1.75 | 313.375 |  | 3378.75 |  | 92.25 |  | 105
2 |  |  | 2 | 1 |  | 90 |  | 70 |  | 20
2.25 |  |  | 2.25 | 1 |  | 90 |  | 70 |  | 20
2.5 |  |  | 2.5 | 1 |  | 90 |  | 70 |  | 20
2.75 |  |  | 2.75 | 1 |  | 90 |  | 70 |  | 20
3 |  |  | 3 | 1 |  | 90 |  | 70 |  | 20
3.25 |  |  | 3.25 | 1 |  | 90 |  | 70 |  | 20
3.5 |  |  | 3.5 | 1 |  | 90 |  | 70 |  | 20
3.75 |  |  | 3.75 | 1 |  | 90 |  | 70 |  | 20
4 |  |  | 4 | 1 |  | 90 |  | 70 |  | 20
Remediation Goal (ug/l) |  |  |  | 1 |  | 90 |  | 70 |  | 20 |  | 5000 |  | 0 |  | 0
|  | 2 |  | 0
|  | 2 |  | 26400

## Well 4
Monitoring Well |  | MW-4 |  | Facility Name |  | ACME |  |  | Baseline Sampling Date |  |  | 2011-01-01
|  |  |  | Facility ID # |  | 123456789 |  |  | System Startup Date |  |  | 2011-01-15
Constituent Concentration Group Milestones (ug/l)
Projected Cleanup Time (yrs) | Actual Sampling Date | Actual Cleanup Time (yrs) |  | Group 1 |  | Group 2 |  | Group 3 |  | Group 4 |  | Group 5 |  | Group 6 |  | Group 7
|  |  |  | Benzene |  | Sum Toluene, Ethylbenzene, & Xylenes |  | Naphthalenes |  | MTBE |  | TRPH |  | PAH (I) |  | PAH (II)
|  |  |  | Proj. | Actual | Proj. | Actual | Proj. | Actual | Proj. | Actual | Proj. | Actual | Proj. | Actual | Proj. | Actual
0 | 2011-01-01 | 0 | 0 | 3200 | 3200 | 18350 | 18350 | 241 | 241 | 600 | 600 | NA | NA | NA | NA | NA | NA
0.25 | 2011-04-16 | 0.24932 | 0.24932 | 2801.2205 |  | 16073.7534 |  | 219.6836 |  | 527.6986
0.5 | 2011-08-05 | 0.55342 | 0.55342 | 2314.7973 |  | 13297.2329 |  | 193.6822 |  | 439.5068
0.75 | 2011-11-01 | 0.79452 | 0.79452 | 1929.1644 |  | 11096.0274 |  | 173.0685 |  | 369.589
1 | 2012-02-02 | 1.0493 | 1.0493 | 1521.6205 |  | 8769.7534 |  | 151.2836 |  | 295.6986
1.25 |  |  | 1.25 | 1200.625 |  | 6937.5 |  | 134.125 |  | 237.5
1.5 |  |  | 1.5 | 800.75 |  | 4655 |  | 112.75 |  | 165
1.75 |  |  | 1.75 | 400.875 |  | 2372.5 |  | 91.375 |  | 92.5
2 |  |  | 2 | 1 |  | 90 |  | 70 |  | 20
2.25 |  |  | 2.25 | 1 |  | 90 |  | 70 |  | 20
2.5 |  |  | 2.5 | 1 |  | 90 |  | 70 |  | 20
2.75 |  |  | 2.75 | 1 |  | 90 |  | 70 |  | 20
3 |  |  | 3 | 1 |  | 90 |  | 70 |  | 20
3.25 |  |  | 3.25 | 1 |  | 90 |  | 70 |  | 20
3.5 |  |  | 3.5 | 1 |  | 90 |  | 70 |  | 20
3.75 |  |  | 3.75 | 1 |  | 90 |  | 70 |  | 20
4 |  |  | 4 | 1 |  | 90 |  | 70 |  | 20
Remediation Goal (ug/l) |  |  |  | 1 |  | 90 |  | 70 |  | 20 |  | 5000 |  | 0 |  | 0
|  | 2 |  | 0
|  | 2 |  | 18350

## Well 5
Monitoring Well |  | MW-5 |  | Facility Name |  | ACME |  |  | Baseline Sampling Date |  |  | 2011-01-01
|  |  |  | Facility ID # |  | 123456789 |  |  | System Startup Date |  |  | 2011-01-15
Constituent Concentration Group Milestones (ug/l)
Projected Cleanup Time (yrs) | Actual Sampling Date | Actual Cleanup Time (yrs) |  | Group 1 |  | Group 2 |  | Group 3 |  | Group 4 |  | Group 5 |  | Group 6 |  | Group 7
|  |  |  | Benzene |  | Sum Toluene, Ethylbenzene, & Xylenes |  | Naphthalenes |  | MTBE |  | TRPH |  | PAH (I) |  | PAH (II)
|  |  |  | Proj. | Actual | Proj. | Actual | Proj. | Actual | Proj. | Actual | Proj. | Actual | Proj. | Actual | Proj. | Actual
0 | 2011-01-01 | 0 | 0 | 21000 | 21000 | 40400 | 40400 | 283 | 283 | 545 | 545 | NA | NA | NA | NA | NA | NA
0.25 | 2011-04-16 | 0.24932 | 0.24932 | 18382.3164 |  | 35375.0548 |  | 256.4479 |  | 479.5548
0.5 | 2011-08-05 | 0.55342 | 0.55342 | 15189.3178 |  | 29245.726 |  | 224.0603 |  | 399.726
0.75 | 2011-11-01 | 0.79452 | 0.79452 | 12657.9315 |  | 24386.4384 |  | 198.3836 |  | 336.4384
1 | 2012-02-02 | 1.0493 | 1.0493 | 9982.7164 |  | 19251.0548 |  | 171.2479 |  | 269.5548
1.25 |  |  | 1.25 | 7875.625 |  | 15206.25 |  | 149.875 |  | 216.875
1.5 |  |  | 1.5 | 5250.75 |  | 10167.5 |  | 123.25 |  | 151.25
1.75 |  |  | 1.75 | 2625.875 |  | 5128.75 |  | 96.625 |  | 85.625
2 |  |  | 2 | 1 |  | 90 |  | 70 |  | 20
2.25 |  |  | 2.25 | 1 |  | 90 |  | 70 |  | 20
2.5 |  |  | 2.5 | 1 |  | 90 |  | 70 |  | 20
2.75 |  |  | 2.75 | 1 |  | 90 |  | 70 |  | 20
3 |  |  | 3 | 1 |  | 90 |  | 70 |  | 20
3.25 |  |  | 3.25 | 1 |  | 90 |  | 70 |  | 20
3.5 |  |  | 3.5 | 1 |  | 90 |  | 70 |  | 20
3.75 |  |  | 3.75 | 1 |  | 90 |  | 70 |  | 20
4 |  |  | 4 | 1 |  | 90 |  | 70 |  | 20
Remediation Goal (ug/l) |  |  |  | 1 |  | 90 |  | 70 |  | 20 |  | 5000 |  | 0 |  | 0
|  | 2 |  | 0
|  | 2 |  | 40400

## Well 6
Monitoring Well |  | MW-6 |  | Facility Name |  | ACME |  |  | Baseline Sampling Date |  |  | 2011-01-01
|  |  |  | Facility ID # |  | 123456789 |  |  | System Startup Date |  |  | 2011-01-15
Constituent Concentration Group Milestones (ug/l)
Projected Cleanup Time (yrs) | Actual Sampling Date | Actual Cleanup Time (yrs) |  | Group 1 |  | Group 2 |  | Group 3 |  | Group 4 |  | Group 5 |  | Group 6 |  | Group 7
|  |  |  | Benzene |  | Sum Toluene, Ethylbenzene, & Xylenes |  | Naphthalenes |  | MTBE |  | TRPH |  | PAH (I) |  | PAH (II)
|  |  |  | Proj. | Actual | Proj. | Actual | Proj. | Actual | Proj. | Actual | Proj. | Actual | Proj. | Actual | Proj. | Actual
0 | 2011-01-01 | 0 | 0 | 16000 | 16000 | 32700 | 32700 | 252 | 252 | 3210 | 3210 | NA | NA | NA | NA | NA | NA
0.25 | 2011-04-16 | 0.24932 | 0.24932 | 14005.6041 |  | 28634.9178 |  | 229.3123 |  | 2812.3425
0.5 | 2011-08-05 | 0.55342 | 0.55342 | 11572.8795 |  | 23676.411 |  | 201.6384 |  | 2327.2877
0.75 | 2011-11-01 | 0.79452 | 0.79452 | 9644.2329 |  | 19745.3425 |  | 179.6986 |  | 1942.7397
1 | 2012-02-02 | 1.0493 | 1.0493 | 7606.0041 |  | 15590.9178 |  | 156.5123 |  | 1536.3425
1.25 |  |  | 1.25 | 6000.625 |  | 12318.75 |  | 138.25 |  | 1216.25
1.5 |  |  | 1.5 | 4000.75 |  | 8242.5 |  | 115.5 |  | 817.5
1.75 |  |  | 1.75 | 2000.875 |  | 4166.25 |  | 92.75 |  | 418.75
2 |  |  | 2 | 1 |  | 90 |  | 70 |  | 20
2.25 |  |  | 2.25 | 1 |  | 90 |  | 70 |  | 20
2.5 |  |  | 2.5 | 1 |  | 90 |  | 70 |  | 20
2.75 |  |  | 2.75 | 1 |  | 90 |  | 70 |  | 20
3 |  |  | 3 | 1 |  | 90 |  | 70 |  | 20
3.25 |  |  | 3.25 | 1 |  | 90 |  | 70 |  | 20
3.5 |  |  | 3.5 | 1 |  | 90 |  | 70 |  | 20
3.75 |  |  | 3.75 | 1 |  | 90 |  | 70 |  | 20
4 |  |  | 4 | 1 |  | 90 |  | 70 |  | 20
Remediation Goal (ug/l) |  |  |  | 1 |  | 90 |  | 70 |  | 20 |  | 5000 |  | 0 |  | 0
|  | 2 |  | 0
|  | 2 |  | 32700