## Storms Sandy-Debby
Conference Report on SB 1500: 2013-14 Beach Projects
(as detailed in specific proviso)
Hurricane Sandy - Federally Authorized (Corps) Projects
|  |  | TOTAL | STATE AMOUNT | LOCAL | FEDERAL * | Amount to be Contracted / Encumbered (State Share) | Date Draft in Process | Date Forward to Sponsor | Date Executed | Comments
Grant # | PROJECT | COUNTY | COSTS | Cost Share | Cost Share | Cost Share
| Brevard North Reach | Brevard | 17000000 | 0 | 0 | 17000000 | 0
| Brevard South Reach | Brevard | 10250000 | 0 | 0 | 10250000 | 0
09SL2 | Ft. Pierce Beach | St Lucie | 7350000 | 350000 | 350000 | 6650000 | 350000 | 2014-03-06 |  | 2014-03-28
| Hutchinson Island | Martin | 3000000 | 0 | 0 | 3000000 | 0
14PB1 | Jupiter/Carlin | Palm Beach | 9000000 | 2500000 | 2500000 | 4000000 | 2500000 | 2013-08-15 | 2013-08-16 | 2013-10-14
| Delray Beach | Palm Beach | 4050000 | 0 | 0 | 4050000 | 0
14PB3 | North Boca Raton | Palm Beach | 6100000 | 790000 | 790000 | 4520000 | 790000 | 2013-08-15 | 2013-08-16 | 2013-09-24
14BO2 | Broward Segment II | Broward | 29400000 | 4700000 | 4700000 | 20000000 | 4700000 | 2014-01-07 | 2014-01-14 | 2014-04-07
| TOTAL |  | 86150000 | 8340000 | 8340000 | 69470000 | 8340000
Tropical Storm Debby - Federally Authorized (Corps) Projects
|  |  | TOTAL | STATE AMOUNT | LOCAL | FEDERAL * | Amount to be Contracted / Encumbered (State Share) | Draft in Process | Forward to Sponsor | Executed | Comments
| PROJECT | COUNTY | COSTS | Cost Share | Cost Share | Cost Share
| Captiva ** | Lee | 18500000 | $4.5m provided in 2012-13 | 6100000 | 7900000
14PI1 | Treasure Island | Pinellas | 12200000 | 2000000 | 2000000 | 8200000 | 2000000 | 2013-08-15 | 2013-08-16 | 2013-10-17
14LE1 | Gasparilla | Lee | 9800000 | 2100000 | 1600000 | 6100000 | 2100000 | 2013-08-12 | 2013-08-13 | 2013-12-09
14ME1 | Anna Maria Island | Manatee | 20000000 | 3175000 | 3175000 | 13650000 | 3175000 | 2013-08-12 | 2013-08-16 | 2013-10-01
| TOTAL |  | 60500000 | 7275000 | 12875000 | 35850000 | 7275000
*Includes 100% federal funding (FCCE) for sand losses and federal cost-sharing for Construction General (CG). The Corps of Engineers has favorably reviewed all projects
and determined funding amounts. Funds are available.
**Captiva not in state appropriation total. Local share may not be accurate based on pre-Debby funding estimates.
Maximize Federal Funds for Other Priority Projects* that Sustained Storm Damages
|  |  | TOTAL | STATE AMOUNT | LOCAL | FEDERAL |  | See Beach Project List Worksheet
| PROJECT | COUNTY | COSTS | Cost Share | Cost Share | Cost Share | #REF!
14PB2 | Ocean Ridge | Palm Beach | 5600000 | 1114000 | 1114000 | 3372000 | 1114000 | 2013-08-15 | 2013-08-16 | 2013-10-14
13ST1 | Venice | Sarasota | 11868000 | 1425000 | 1425000 | 9018000 | 1425000 | 2013-09-13 | 2013-10-09 | 2013-11-21
14PI2 | Long Key | Pinellas | 9048000 | 1774000 | 1774000 | 5500000 | 1774000 | 2013-08-15 | 2013-08-16 | 2013-10-21
| TOTAL |  | 26516000 | 4313000 | 4313000 | 17890000 | 4313000
*FY 2013-14 Dept. of Environmental Protection Priority Project List. Projects are currently being considered for federal construction cost-share and are critically eroded beaches.
| TOTALSTORM-DAMAGED PROJECTS THAT MAXIMIZE FEDERAL FUNDS |  | 173166000 | 19928000 | 25528000 | 123210000
| Inlet Management Projects* |  |  | 1992800 |  |  | 3274852.75 | See Inlet Worksheet
*Three highest-ranked inlet projects on the DEP priority list - St. Lucie, Lake Worth, and Sebastian inlet projects.
Inlet funding for these projects shall be proportionately allocated based upon original amounts requested for state cost-sharing.
| Required Post Construction Monitoring |  |  | 1100000 |  |  | 1100000 | See Post Construction Worksheet
| TOTAL STORM-DAMAGED PROJECTS THAT MAXIMIZE FEDERAL FUNDS & OTHER STATUTORY REQUIREMENTS |  | 173166000 | 23020800 | 25528000 | 123210000
Hurricane Sandy - Non-Federal Beach Nourishment Projects - FEMA Alternative
|  |  |  | STATE AMOUNT | LOCAL AMOUNT | FEDERAL | Amount to be Contracted / Encumbered (State Share) | Draft in Process | Forward to Sponsor | Executed | Comments
|  |  | TOTAL | 50% | 50% | AMOUNT *
| PROJECT | COUNTY | COSTS | Cost Share | Cost Share
14BE1 | Mid-reach & Southern Beaches | Brevard | 10300000 | 5150000 | 5150000 | 0 | 4560663.98 | 2014-02-24 | 2014-03-05 | 2014-03-28
14IRI | Sebastian Inlet State Park | Indian River | 9675000 | 2137500 | 4837500 | 0 | 2137500 | 2013-09-09 | 2013-11-05 | 2013-11-20
14IR2 | Indian River County Sector | Indian River |  | 2700000 |  |  | 2700000 | 2013-10-17 | 2013-10-21 | 2013-11-22
14SL1 | South St. Lucie Dune Restoration | St. Lucie | 500000 | 250000 | 250000 | 0 | 250000 | 2014-02-17 | 2014-02-24 | 2014-03-28
14MI1 | Jupiter Island | Martin | 3600000 | 1600000 | 1600000 | 0 | 231685.4 | 2014-07-21 | 2014-07-22 | 2014-08-01
14MI2 | Jupiter Island | Martin |  |  |  |  | 1368314.6 | 2014-11-14 | 2014-11-14 | 2014-12-05
12MI2 | Bathtub Beach |  |  | 200000 | 200000 | 0 | 200000 | 2013-06-13 | 2013-09-20 | 2013-10-30
14PB5 | Singer Island | Palm Beach | 1100000 | 550000 | 550000 | 0 | 550000 | 2013-09-23 | 2013-10-07 | 2014-03-28
14PB4 | Coral Cove | Palm Beach | 300000 | 150000 | 150000 | 0 | 150000 | 2013-09-05 | 2013-09-10 | 2013-11-06
14BO3 | Deerfield Beach | Broward | 1400000 | 700000 | 700000 | 0 | 700000 | 2014-03-03 | 2014-03-10 | 2014-04-16 | In facts
| TOTAL |  | 26875000 | 13437500 | 13437500 | 0 | 12848163.98
*Governor's request and appeal for FEMA funding denied. This list represents selected state/local projects that would have been eligible for FEMA Cat G sand loss funding.
DEP statewide BMFAP
14CO1 | Collier County Beach Nourishment Project* |  |  | 998000 |  |  | 305283.27 | 2014-10-24 | 2014-10-28 | 2015-01-15
*State cost share estimated. Local cost-share shall be based on contractual project eligibility.
| GRAND TOTAL ALL PROJECTS |  | 200041000 | 37456300 | 38965500 | 123210000 | 37456300
|  |  | GENERAL REVENUE NEW | 15102200 |  | Total Remaining | 0
|  |  | GENERAL REVENUE REVERSIONS | 3116092
|  |  | Subtotal GR | 18218292
|  |  | ECOSYSTEM TF NEW | 11668792
|  |  | ECOSYSTEM TF REVERSIONS | 7569216
|  |  | Subtotal TF | 19238008
|  |  | TOTAL ALL FUNDS | 37456300

## Inlet Mangement Plan
Contract Number | Project Name | Sponsor |  | Amount per LBR (State Share) | Amount Appropriated (State Share) | Amount to be Contracted / Encumbered (State Share) | Draft in Process | Forward to Sponsor | Executed | Comments
Inlet Sand Bypassing/Inlet Management Plan Implementation Projects
| Inlet and Southeast Regional Sediment Management | FDEP | D | 500000
13MI1/A1 | St. Lucie Inlet IMP Implementation | Martin County | C | 1556250 | 1419300 | 1419300 | 2014-03-17 | 2014-03-19 | 2014-03-28
14PB7 | Lake Worth Inlet Federal Bypassing | Town of Palm Beach | C | 24750 | 22572 | 22572 | 2014-09-22 | 2014-09-25 | 2014-12-19
08IR1A5 | Sebastian IMP Implementation | Sebastian Inlet District | C | 603750 | 550620 | 550620 | 2013-09-13 | 2013-10-02 | 2013-10-14
| Port Canaveral IMP Implementation | Canaveral Port Authority | F/D | 88500
14LE3 | Blind Pass | Lee County | C | 1211250 |  | 156021.6 | 2014-11-19 | 2014-11-20 | 2015-01-22
| St. Andrew's Inlet IMP Implementation | FDEP- Parks | C | 2305000
14ME3 | Longboat Pass IMP Implementation | WCIND, Town and County | C | 1614866 |  | 57381 | 2014-11-18 | 2014-11-21 | 2014-12-15
14ME4 | Manatee County |  |  |  |  | 62788 | 2014-11-19 | 2014-11-21 | 2014-12-22
08ME1 | Longboat Pass IMP Implementation |  |  |  |  | 706170 | 2014-11-19 | 2014-12-05 | 2014-12-05
| Ft. Pierce Inlet IMP Implementation | St. Lucie County | D | 37500
| South Lake Worth Inlet IMP Implementation | Palm Beach County | D | 112500
| Ft. Clinch Inlet Sand Transfer | FDEP- Parks | F | 100000
| Mexico Beach IMP Implementation | Town of Mexico Beach | C | 179250
| Venice Inlet IMP Implementation | WCIND | C | 277500
| Boca Inlet IMP Implementation | City of Boca Raton | C | 360450
| Sand Source Mangement--300,000 |  |  | 300000
| BS029 Task 13 |  |  |  |  | 100000 |  |  | 2014-12-19
| BS028 Task 4 |  |  |  |  | 200000.15 |  |  | 2015-01-12
|  | Totals: |  | 9271566 | 1992492 | 3274852.75
Inlet funds
Per proviso, funds were apportioned at 91.2%.

## Post-Const. Mon
Cont # | Project Name | Amount per LBR (State Share) | Amount Currently Appropriated | Prorated Amount | Amount to be Encumbered | Draft Date | Forwarded to Sponsor | Executed | Comments
1100000
2nd+ YEAR POST-CONSTRUCTION MONITORING-
09SL2 | Ft. Pierce Shore Protection Project | 150000 |  |  | 69869 | 2014-03-06 |  | 2014-03-28
| North/South Reaches- Brevard County Shore Protection Project | 81795 | [6 empty] | Adequate funds in contract
11SJ1/A1 | St. Johns County Shore Protection Project | 91773 |  |  | 60959 | 2014-08-07 |  | 2014-08-20
| Anna Maria Island/ Manatee County Shore Protection Project | 150350 | [6 empty] | Adequate funds in contract
| Duval County Shore Protection Project | 42489 | [6 empty] | Adequate funds in contract
10PB4 | North Boca Raton Shore Protection Project | 11800 |  |  | 38462 |  |  | 2013-09-13
09LE2 | Estero Island - Lee County Shore Protection Project | 22500 |  |  | 10881 | 2014-10-22 | 2014-10-29 | 2015-01-05 | Remainder not required
| Delray Beach Shore Protection Project | 23680 | [6 empty] | Adequate funds in contract
| Lido Beach Nourishment | 30000 | [6 empty] | Adequate funds in contract
14NA1 | South Amelia Island Beach Nourishment | 95594 |  |  | 89637.5 | 2014-10-06 | 2014-10-10 | 2014-12-03 | Remainder not required
| Bathtub Beach Restoration | 87500 | [6 empty] | Adequate funds in contract
13GU1 | St. Joseph Peninsula Beach Restoration | 74445 |  |  | 4380.33 | 2014-08-13 | 2014-08-14 | 2014-12-19 | Remainder not required
14IR3 | Wabasso Beach Restoration | 275000 |  |  | 223386.39 | 2014-10-02 | 2014-10-10 | 2014-11-14 | Remainder not required
14WL1 | Western Walton Beach Restoration | 34925 |  |  | 33961 | 2014-11-07 | 2014-11-07 | 2015-01-05 | Remainder not required
14ME2 | Longboat Key Beach Nourishment | 96858 |  |  | 96858 | 2014-10-16 | 2014-10-17 | 2014-12-15
14ES1 | Pensacola Beach Nourishment | 52750 |  |  | 52750 | 2014-11-07 | 2014-11-10 | 2014-12-19
| Collier County Beach Nourishment | 72540 | [6 empty] | Adequate funds in contract
| Bonita Beach Nourishment | 13562 | [6 empty] | Adequate funds in contract
14MI2 | Jupiter Island Beach Nourishment | 82438 |  |  | 82432 | 2014-11-14 | 2014-11-14 | 2014-12-14
| Juno Beach Nourishment | 125000 | [6 empty] | Adequate funds in contract
| South Marco Island Beach Nourishment | 16158 | [6 empty] | Adequate funds in contract
14CH1 | Charlotte County Beach Restoration | 404076 |  |  | 304906.57 | 2014-11-12 | 2014-11-13 | 14/19/14 | Remainder not required | 0
14PB8 | Mid-Town Beach Nourishment | 94334 |  |  | 31517.21 | 2014-11-18 | 2014-11-19 | 14/19/14
| Hollywood Beach Nourishment | 36480
| South Boca Raton Beach Nourishment | 7090
| Hillsboro Beach Nourishment | 38580
|  | 2211717 | 0 |  | 1100000
Holding formula if fund all @50%
0